## Summary
(Example Client) — ISO 42001 readiness workbook
(Example Client) · ISO 42001 · generated from the GRC record as of 2026-10-24. Read-only export: change the record through pull requests, not here.
As of | 2026-10-24 | The date the record was evaluated; overdue figures count from here.
Applicable requirements
Requirements ready |  | Every leg verified on current evidence.
Share ready
Evidence-test legs verified |  | Out of 4 per applicable requirement.
Share of legs verified
Open gaps |  | Open or in progress.
Overdue gaps |  | Open or in progress and past their due date.
Open nonconformities (major)
Open nonconformities (minor)
Evidence failing or expired
AI systems with a current, approved impact assessment |  | Out of 0 AI systems in scope.
Policies and procedures current and approved |  | Out of 17 in the library.
Management review actions open

## Control matrix
(Example Client) · ISO 42001 · generated from the GRC record as of 2026-10-24. Read-only export: change the record through pull requests, not here.
ID | Requirement | Type | Applicable | Owner | Documented | Implemented | Evidenced | Tested | State | Gaps | Evidence
4.1 | Understanding the organization and its context | Clause | Yes | Legal | partial | claimed | not_started | not_started | In progress | GAP-07 | EV-001
4.2 | Understanding the needs and expectations of interested parties | Clause | Yes | Legal | claimed | not_started | not_started | not_started | Unverified claim | GAP-07
4.3 | Determining the scope of the AI management system | Clause | Yes | VP Engineering | partial | not_started | not_started | not_started | In progress | GAP-01 | EV-001
4.4 | AI management system | Clause | Yes | VP Engineering | not_started | not_started | not_started | not_started | Not started
5.1 | Leadership and commitment | Clause | Yes | VP Engineering | claimed | partial | not_started | not_started | In progress | GAP-09 | EV-016
5.2 | AI policy | Clause | Yes | VP Engineering | not_started | not_started | not_started | not_started | Not started | GAP-01
5.3 | Roles, responsibilities and authorities | Clause | Yes | VP Engineering | claimed | not_started | not_started | not_started | Unverified claim | GAP-11
6.1.1 | Actions to address risks and opportunities - general | Clause | Yes | Security & Compliance | partial | not_started | not_started | not_started | In progress |  | EV-005
6.1.2 | AI risk assessment | Clause | Yes | Security & Compliance | partial | verified | verified | not_started | In progress |  | EV-004, EV-005
6.1.3 | AI risk treatment | Clause | Yes | Security & Compliance | not_started | partial | not_started | not_started | In progress | GAP-10 | EV-004
6.1.4 | AI system impact assessment | Clause | Yes | Head of Responsible AI | not_started | not_started | not_started | not_started | Not started | GAP-02
6.2 | AI objectives and planning to achieve them | Clause | Yes | VP Engineering | not_started | not_started | not_started | not_started | Not started
6.3 | Planning of changes | Clause | Yes | VP Engineering | not_started | not_started | not_started | not_started | Not started
7.1 | Resources | Clause | Yes | VP Engineering | claimed | not_started | not_started | not_started | Unverified claim
7.2 | Competence | Clause | Yes | People Operations | not_started | not_started | not_started | not_started | Not started | GAP-03
7.3 | Awareness | Clause | Yes | People Operations | not_started | partial | not_started | not_started | In progress | GAP-03 | EV-021
7.4 | Communication | Clause | Yes | VP Engineering | not_started | not_started | not_started | not_started | Not started
7.5 | Documented information | Clause | Yes | Security & Compliance | verified | claimed | not_started | not_started | In progress |  | EV-020
8.1 | Operational planning and control | Clause | Yes | Head of Platform | partial | partial | not_started | not_started | In progress | GAP-05 | EV-008, EV-009
8.2 | AI risk assessment (operation) | Clause | Yes | Security & Compliance | partial | verified | verified | not_started | In progress |  | EV-004, EV-005
8.3 | AI risk treatment (operation) | Clause | Yes | Security & Compliance | not_started | partial | not_started | not_started | In progress |  | EV-004
8.4 | AI system impact assessment (operation) | Clause | Yes | Head of Responsible AI | not_started | not_started | not_started | not_started | Not started | GAP-02
9.1 | Monitoring, measurement, analysis and evaluation | Clause | Yes | Head of Platform | not_started | partial | not_started | not_started | In progress |  | EV-012
9.2 | Internal audit | Clause | Yes | Security & Compliance | not_started | not_started | not_started | not_started | Not started | GAP-08
9.3 | Management review | Clause | Yes | VP Engineering | not_started | partial | not_started | not_started | In progress | GAP-09 | EV-016
10.1 | Continual improvement | Clause | Yes | VP Engineering | not_started | not_started | not_started | not_started | Not started
10.2 | Nonconformity and corrective action | Clause | Yes | Security & Compliance | verified | partial | not_started | not_started | In progress |  | EV-013, EV-014
A.2.2 | AI policy | Annex A | Yes | VP Engineering | not_started | not_started | not_started | not_started | Not started | GAP-01
A.2.3 | Alignment with other organizational policies | Annex A | Yes | Security & Compliance | not_started | not_started | not_started | not_started | Not started
A.2.4 | Review of the AI policy | Annex A | Yes | Security & Compliance | not_started | not_started | not_started | not_started | Not started
A.3.2 | AI roles and responsibilities | Annex A | Yes | VP Engineering | claimed | not_started | not_started | not_started | Unverified claim | GAP-11
A.3.3 | Reporting of concerns | Annex A | Yes | Legal | not_started | not_started | not_started | not_started | Not started | GAP-12
A.4.2 | Resource documentation | Annex A | Yes | Head of Platform | partial | verified | partial | not_started | In progress |  | EV-001, EV-002, EV-003
A.4.3 | Data resources | Annex A | Yes | Head of Platform | claimed | not_started | not_started | not_started | Unverified claim | GAP-04
A.4.4 | Tooling resources | Annex A | Yes | Head of Platform | not_started | claimed | not_started | not_started | Unverified claim
A.4.5 | System and computing resources | Annex A | Yes | Head of Platform | not_started | claimed | not_started | not_started | Unverified claim
A.4.6 | Human resources | Annex A | Yes | People Operations | not_started | not_started | not_started | not_started | Not started | GAP-03
A.5.2 | AI system impact assessment process | Annex A | Yes | Head of Responsible AI | not_started | not_started | not_started | not_started | Not started | GAP-02
A.5.3 | Documentation of AI system impact assessments | Annex A | Yes | Head of Responsible AI | not_started | not_started | not_started | not_started | Not started | GAP-02
A.5.4 | Assessing AI system impact on individuals or groups of individuals | Annex A | Yes | Head of Responsible AI | not_started | not_started | not_started | not_started | Not started | GAP-02
A.5.5 | Assessing societal impacts of AI systems | Annex A | Yes | Head of Responsible AI | not_started | not_started | not_started | not_started | Not started | GAP-02
A.6.1.2 | Objectives for responsible development of AI system | Annex A | Yes | Head of Responsible AI | partial | not_started | not_started | not_started | In progress |  | EV-006
A.6.1.3 | Processes for responsible AI system design and development | Annex A | Yes | Head of Platform | partial | partial | not_started | not_started | In progress | GAP-06 | EV-008, EV-009
A.6.2.2 | AI system requirements and specification | Annex A | Yes | Head of Platform | not_started | claimed | not_started | not_started | Unverified claim
A.6.2.3 | Documentation of AI system design and development | Annex A | Yes | Head of Platform | not_started | claimed | not_started | not_started | Unverified claim
A.6.2.4 | AI system verification and validation | Annex A | Yes | Head of Platform | claimed | verified | verified | partial | In progress | GAP-06 | EV-009, EV-010, EV-011, EV-022
A.6.2.5 | AI system deployment | Annex A | Yes | Head of Platform | claimed | verified | verified | not_started | In progress | GAP-06 | EV-009, EV-011
A.6.2.6 | AI system operation and monitoring | Annex A | Yes | Head of Platform | not_started | verified | partial | not_started | In progress |  | EV-012
A.6.2.7 | AI system technical documentation | Annex A | Yes | Head of Platform | not_started | not_started | not_started | not_started | Not started
A.6.2.8 | AI system recording of event logs | Annex A | Yes | Head of Platform | not_started | verified | partial | not_started | In progress |  | EV-019
A.7.2 | Data for development and enhancement of AI system | Annex A | Yes | Security & Compliance | partial | not_started | not_started | not_started | In progress | GAP-04 | EV-017
A.7.3 | Acquisition of data | Annex A | Yes | Head of Platform | not_started | not_started | not_started | not_started | Not started
A.7.4 | Quality of data for AI systems | Annex A | Yes | Head of Platform | not_started | claimed | not_started | not_started | Unverified claim | GAP-04
A.7.5 | Data provenance | Annex A | Yes | Head of Platform | claimed | verified | verified | not_started | In progress | GAP-06 | EV-018
A.7.6 | Data preparation | Annex A | Yes | Head of Platform | not_started | not_started | not_started | not_started | Not started
A.8.2 | System documentation and information for users | Annex A | Yes | Head of Platform | not_started | not_started | not_started | not_started | Not started
A.8.3 | External reporting | Annex A | Yes | Legal | not_started | not_started | not_started | not_started | Not started | GAP-12
A.8.4 | Communication of incidents | Annex A | Yes | Security & Compliance | partial | partial | not_started | not_started | In progress |  | EV-013, EV-014
A.8.5 | Information for interested parties | Annex A | Yes | Legal | not_started | not_started | not_started | not_started | Not started | GAP-07
A.9.2 | Processes for responsible use of AI systems | Annex A | Yes | Security & Compliance | partial | not_started | not_started | not_started | In progress |  | EV-007
A.9.3 | Objectives for responsible use of AI system | Annex A | Yes | Head of Responsible AI | not_started | not_started | not_started | not_started | Not started
A.9.4 | Intended use of the AI system | Annex A | Yes | Head of Platform | not_started | claimed | not_started | not_started | Unverified claim | GAP-06
A.10.2 | Allocating responsibilities | Annex A | Yes | Legal | not_started | not_started | not_started | not_started | Not started | GAP-05
A.10.3 | Suppliers | Annex A | Yes | Security & Compliance | partial | not_started | not_started | not_started | In progress | GAP-05 | EV-015
A.10.4 | Customers | Annex A | Yes | Legal | not_started | not_started | not_started | not_started | Not started

## SoA
(Example Client) · ISO 42001 · generated from the GRC record as of 2026-10-24. Read-only export: change the record through pull requests, not here.
Control | Title | Applicable | Justification | Implementation | State | Owner
A.2.2 | AI policy | Yes | Included: in scope for AI products built and provided by the Innovation and Platform teams. |  | Not started | VP Engineering
A.2.3 | Alignment with other organizational policies | Yes | Included: in scope for AI products built and provided by the Innovation and Platform teams. |  | Not started | Security & Compliance
A.2.4 | Review of the AI policy | Yes | Included: in scope for AI products built and provided by the Innovation and Platform teams. |  | Not started | Security & Compliance
A.3.2 | AI roles and responsibilities | Yes | Included: in scope for AI products built and provided by the Innovation and Platform teams. |  | Unverified claim | VP Engineering
A.3.3 | Reporting of concerns | Yes | Included: in scope for AI products built and provided by the Innovation and Platform teams. |  | Not started | Legal
A.4.2 | Resource documentation | Yes | Included: in scope for AI products built and provided by the Innovation and Platform teams. | AI systems inventory and model registry. | In progress | Head of Platform
A.4.3 | Data resources | Yes | Included: in scope for AI products built and provided by the Innovation and Platform teams. |  | Unverified claim | Head of Platform
A.4.4 | Tooling resources | Yes | Included: in scope for AI products built and provided by the Innovation and Platform teams. | 9 SDLC AI tools listed in the inventory workbook. | Unverified claim | Head of Platform
A.4.5 | System and computing resources | Yes | Included: in scope for AI products built and provided by the Innovation and Platform teams. | 10 infrastructure services listed in the inventory workbook. | Unverified claim | Head of Platform
A.4.6 | Human resources | Yes | Included: in scope for AI products built and provided by the Innovation and Platform teams. |  | Not started | People Operations
A.5.2 | AI system impact assessment process | Yes | Included: in scope for AI products built and provided by the Innovation and Platform teams. |  | Not started | Head of Responsible AI
A.5.3 | Documentation of AI system impact assessments | Yes | Included: in scope for AI products built and provided by the Innovation and Platform teams. |  | Not started | Head of Responsible AI
A.5.4 | Assessing AI system impact on individuals or groups of individuals | Yes | Included: in scope for AI products built and provided by the Innovation and Platform teams. |  | Not started | Head of Responsible AI
A.5.5 | Assessing societal impacts of AI systems | Yes | Included: in scope for AI products built and provided by the Innovation and Platform teams. |  | Not started | Head of Responsible AI
A.6.1.2 | Objectives for responsible development of AI system | Yes | Included: in scope for AI products built and provided by the Innovation and Platform teams. | Responsible AI Principles serve as development objectives. | In progress | Head of Responsible AI
A.6.1.3 | Processes for responsible AI system design and development | Yes | Included: in scope for AI products built and provided by the Innovation and Platform teams. | AI SDLC procedure drafted from existing engineering practice. | In progress | Head of Platform
A.6.2.2 | AI system requirements and specification | Yes | Included: in scope for AI products built and provided by the Innovation and Platform teams. |  | Unverified claim | Head of Platform
A.6.2.3 | Documentation of AI system design and development | Yes | Included: in scope for AI products built and provided by the Innovation and Platform teams. |  | Unverified claim | Head of Platform
A.6.2.4 | AI system verification and validation | Yes | Included: in scope for AI products built and provided by the Innovation and Platform teams. | CI gate blocks release unless evaluation metrics meet thresholds. | In progress | Head of Platform
A.6.2.5 | AI system deployment | Yes | Included: in scope for AI products built and provided by the Innovation and Platform teams. | Production promotion requires an approved PR and passing gate. | In progress | Head of Platform
A.6.2.6 | AI system operation and monitoring | Yes | Included: in scope for AI products built and provided by the Innovation and Platform teams. | Production telemetry for drift and error rates. | In progress | Head of Platform
A.6.2.7 | AI system technical documentation | Yes | Included: in scope for AI products built and provided by the Innovation and Platform teams. |  | Not started | Head of Platform
A.6.2.8 | AI system recording of event logs | Yes | Included: in scope for AI products built and provided by the Innovation and Platform teams. | Event logging configured for AI services in Terraform. | In progress | Head of Platform
A.7.2 | Data for development and enhancement of AI system | Yes | Included: in scope for AI products built and provided by the Innovation and Platform teams. |  | In progress | Security & Compliance
A.7.3 | Acquisition of data | Yes | Included: the Platform team acquires third-party and customer data for model development. |  | Not started | Head of Platform
A.7.4 | Quality of data for AI systems | Yes | Included: in scope for AI products built and provided by the Innovation and Platform teams. |  | Unverified claim | Head of Platform
A.7.5 | Data provenance | Yes | Included: in scope for AI products built and provided by the Innovation and Platform teams. | Datasets and checkpoints hashed at ingest; manifests stored with artifacts. | In progress | Head of Platform
A.7.6 | Data preparation | Yes | Included: in scope for AI products built and provided by the Innovation and Platform teams. |  | Not started | Head of Platform
A.8.2 | System documentation and information for users | Yes | Included: in scope for AI products built and provided by the Innovation and Platform teams. |  | Not started | Head of Platform
A.8.3 | External reporting | Yes | Included: in scope for AI products built and provided by the Innovation and Platform teams. |  | Not started | Legal
A.8.4 | Communication of incidents | Yes | Included: in scope for AI products built and provided by the Innovation and Platform teams. | SOC 2 incident process includes customer notification. | In progress | Security & Compliance
A.8.5 | Information for interested parties | Yes | Included: in scope for AI products built and provided by the Innovation and Platform teams. |  | Not started | Legal
A.9.2 | Processes for responsible use of AI systems | Yes | Included: in scope for AI products built and provided by the Innovation and Platform teams. | Company AI Use Policy covers end-user use; producer-side use not addressed. | In progress | Security & Compliance
A.9.3 | Objectives for responsible use of AI system | Yes | Included: in scope for AI products built and provided by the Innovation and Platform teams. |  | Not started | Head of Responsible AI
A.9.4 | Intended use of the AI system | Yes | Included: in scope for AI products built and provided by the Innovation and Platform teams. | Agent authority limits enforced in configuration. | Unverified claim | Head of Platform
A.10.2 | Allocating responsibilities | Yes | Included: in scope for AI products built and provided by the Innovation and Platform teams. |  | Not started | Legal
A.10.3 | Suppliers | Yes | Included: in scope for AI products built and provided by the Innovation and Platform teams. | SOC 2 vendor program exists; AI suppliers not yet reviewed through it. | In progress | Security & Compliance
A.10.4 | Customers | Yes | Included: AI products are delivered to government customers with contractual AI requirements. |  | Not started | Legal

## Gaps
(Example Client) · ISO 42001 · generated from the GRC record as of 2026-10-24. Read-only export: change the record through pull requests, not here.
ID | Area | Finding | Requirements | Owner | Due | Phase | Severity | Status | Days overdue
GAP-01 | AIMS governance | No producer-scope AIMS AI policy yet; scope draft still needs leadership approval. | 5.2, 4.3, A.2.2 | VP Engineering | 2026-11-20 | governance | high | open
GAP-02 | Impact assessment | No AI impact assessments have been completed; methodology/template must be established and used. | 6.1.4, 8.4, A.5.2, A.5.3, A.5.4, A.5.5 | Head of Responsible AI | 2026-12-18 | implement | high | open
GAP-03 | Training & competence | AI-specific training is planned but not yet operating. | 7.2, 7.3, A.4.6 | People Operations | 2026-12-18 | implement | medium | open
GAP-04 | Data governance | Existing classification taxonomy does not yet cover AI artifacts such as corpora, datasets, checkpoints, and delivered models. | A.4.3, A.7.2, A.7.4 | Security & Compliance | 2026-11-25 | governance | medium | open
GAP-05 | AI suppliers | AI-specific suppliers have not yet been run through the existing vendor program; supplier contract/DPA requirements are incomplete. | A.10.2, A.10.3, 8.1 | Security & Compliance | 2026-12-18 | implement | high | open
GAP-06 | Control codification | Some human-review and engineering practices operate in code/process but are not fully reflected in policy text. | A.6.1.3, A.6.2.4, A.6.2.5, A.7.5, A.9.4 | Head of Platform | 2026-11-30 | governance | medium | in_progress
GAP-07 | Regulatory mapping | Formal per-market AI regulatory/contractual mapping has not yet been performed. | 4.1, 4.2, A.8.5 | Legal | 2026-11-30 | governance | medium | open
GAP-08 | Internal audit | No standalone AI/AIMS internal audit program or completed AI-scoped internal audit exists. | 9.2 | Security & Compliance | 2027-01-22 | test | high | open
GAP-09 | Management review | AI is discussed in quarterly leadership review, but a dedicated standing AI/AIMS review structure needs to be formalized. | 9.3, 5.1 | VP Engineering | 2027-01-29 | test | medium | open
GAP-10 | Statement of Applicability | No SoA exists; Annex A applicability and justifications must be decided and approved. | 6.1.3 | Security & Compliance | 2026-11-20 | governance | high | open
GAP-11 | Roles | AIMS roles and responsibilities are not documented in a RACI. | 5.3, A.3.2 | VP Engineering | 2026-11-13 | governance | medium | open
GAP-12 | Concern reporting | No internal or external channel for reporting AI concerns or adverse impacts. | A.3.3, A.8.3 | Legal | 2026-12-11 | implement | medium | open
GAP-13 | Inventory | Model registry entries lacked an accountable owner field. | A.4.2 | Head of Platform | 2026-10-09 | validate | low | closed

## Evidence
(Example Client) · ISO 42001 · generated from the GRC record as of 2026-10-24. Read-only export: change the record through pull requests, not here.
ID | Title | Type | Location | Collected | Expires | Status | Approved by | Supports
EV-001 | Draft AIMS scope statement (unapproved) | document | sharepoint://aims/AIMS-Scope-DRAFT-v0.3.docx | 2026-10-05 | 2027-10-05 | current |  | 4.1·D, 4.3·D, A.4.2·D
EV-002 | AI systems inventory (4 systems) | record | sharepoint://aims/AI-Inventory.xlsx#Systems | 2026-10-05 | 2027-01-03 | current |  | A.4.2·I
EV-003 | Model registry export with owner field populated | record | model-registry://exports/2026-10-07.json | 2026-10-07 | 2027-01-05 | current |  | A.4.2·I, A.4.2·E
EV-004 | Drata AI-category risk register export (20 risks) | record | drata://risks?category=AI (export 2026-09-30) | 2026-09-30 | 2027-01-28 | current |  | 6.1.2·I, 6.1.2·E, 6.1.3·I, 8.2·I, 8.2·E, 8.3·I
EV-005 | Enterprise risk management methodology (SOC 2) | document | sharepoint://policies/ERM-Methodology-v3.pdf | 2026-10-02 | 2027-10-02 | current | CISO | 6.1.1·D, 6.1.2·D, 8.2·D
EV-006 | Responsible AI Principles (published 2025) | document | sharepoint://policies/Responsible-AI-Principles.pdf | 2025-06-01 | 2026-06-01 | EXPIRED | CEO | A.6.1.2·D
EV-007 | Company AI Use Policy (end-user use) | document | sharepoint://policies/AI-Use-Policy-v1.2.pdf | 2026-10-02 | 2027-10-02 | current | CISO | A.9.2·D
EV-008 | AI lifecycle controls procedure (draft) | document | sharepoint://aims/AI-Lifecycle-Controls-Procedure-DRAFT.docx | 2026-10-05 | 2027-10-05 | current |  | 8.1·D, A.6.1.3·D
EV-009 | CI model release and evidence gate (workflow config) | config | git://client-platform/ml-release/.ci/release-gate.yml@main | 2026-10-05 | 2027-01-03 | current |  | 8.1·I, A.6.1.3·I, A.6.2.4·I, A.6.2.5·I
EV-010 | Gated evaluation results - last 3 production releases | record | ci://ml-release/release-gate/runs?branch=main&last=3 | 2026-09-28 | 2026-12-27 | current |  | A.6.2.4·I, A.6.2.4·E
EV-011 | PR approval records for Q3 model promotions | record | github://pulls?label=model-promotion&merged=2026-07-01..2026-09-30 | 2026-10-01 | 2027-01-29 | current |  | A.6.2.4·E, A.6.2.5·I, A.6.2.5·E
EV-012 | Production telemetry dashboard (model drift and error rates) | screenshot | grafana://dashboards/ai-prod-overview (captured 2026-10-03) | 2026-10-03 | 2026-12-02 | current |  | 9.1·I, A.6.2.6·I, A.6.2.6·E
EV-013 | Incident management and corrective action procedure (SOC 2) | document | sharepoint://policies/Incident-Management-v4.pdf | 2026-10-02 | 2027-10-02 | current | CISO | 10.2·D, A.8.4·D
EV-014 | Incident tickets sample, Q3 2026 (includes 1 AI-related) | record | jira://INC?created=2026-07-01..2026-09-30 | 2026-10-02 | 2027-01-30 | current |  | 10.2·I, A.8.4·I
EV-015 | Vendor management procedure (SOC 2) | document | sharepoint://policies/Vendor-Management-v2.pdf | 2026-10-02 | 2027-10-02 | current | CISO | A.10.3·D
EV-016 | Quarterly leadership review minutes, Q3 2026 (AI agenda item) | record | sharepoint://leadership/QBR-2026-Q3-minutes.docx | 2026-10-01 | 2027-01-29 | current |  | 5.1·I, 9.3·I
EV-017 | Data classification policy (SOC 2) - no AI artifact classes | document | sharepoint://policies/Data-Classification-v3.pdf | 2026-10-02 | 2027-10-02 | current | CISO | A.7.2·D
EV-018 | Training-data provenance hash manifests (sample of 3 datasets) | record | s3://ml-artifacts/provenance/manifests/ (sample 2026-10-04) | 2026-10-04 | 2027-01-02 | current |  | A.7.5·I, A.7.5·E
EV-019 | Production event-logging configuration for AI services | config | infra://terraform/modules/ai-services/logging.tf@a1b2c3d | 2026-10-04 | 2027-01-02 | current |  | A.6.2.8·I, A.6.2.8·E
EV-020 | Document control procedure (SOC 2) | document | sharepoint://policies/Document-Control-v2.pdf | 2026-10-02 | 2027-10-02 | current | CISO | 7.5·D
EV-021 | Security awareness training completions (FY26) | record | lms://reports/security-awareness-2026 | 2026-10-02 | 2027-01-30 | current |  | 7.3·I
EV-022 | Analyst walkthrough: release gate on 2 sampled promotions | test | workpapers/WP-01-release-gate-walkthrough.md | 2026-10-07 | 2027-04-05 | current |  | A.6.2.4·T
EV-101 | Engagement repo: main branch protection | config | engagement/evidence/collected/EV-101.json | 2026-10-08 | 2026-11-07 | current |  | (unused)
EV-102 | Engagement repo: independent review of merged changes (90 days) | record | engagement/evidence/collected/EV-102.json | 2026-10-08 | 2026-11-07 | FAILING |  | (unused)
EV-103 | Engagement repo: validation gate runs | record | engagement/evidence/collected/EV-103.json | 2026-10-08 | 2026-11-07 | current |  | (unused)

## Findings
(Example Client) · ISO 42001 · generated from the GRC record as of 2026-10-24. Read-only export: change the record through pull requests, not here.
ID | Grade | Source | Requirement | Status | Owner | Due | Description | Root cause | Corrective action

## Impact assessments
(Example Client) · ISO 42001 · generated from the GRC record as of 2026-10-24. Read-only export: change the record through pull requests, not here.
System | Name | Risk tier | Assessment | Status | Decision | Highest residual | Band | Next review | Current and approved

## Documents
(Example Client) · ISO 42001 · generated from the GRC record as of 2026-10-24. Read-only export: change the record through pull requests, not here.
ID | Title | Type | Status | Version | Owner | Approver | Approved | Next review | Current and approved | Requirements
DOC-SCOPE | AIMS Scope and Context | policy | missing | [5 empty] | No | 4.1, 4.2, 4.3, 4.4
DOC-AI-POLICY | AI Policy | policy | missing | [5 empty] | No | 5.1, 5.2, A.2.2, A.2.3, A.2.4
DOC-ROLES | AI Roles, Responsibilities and Reporting of Concerns | procedure | missing | [5 empty] | No | 5.3, A.3.2, A.3.3, A.10.2
DOC-RISK | AI Risk Management Procedure | procedure | missing | [5 empty] | No | 6.1.1, 6.1.2, 6.1.3, 8.2, 8.3
DOC-IMPACT | AI System Impact Assessment Procedure | procedure | missing | [5 empty] | No | 6.1.4, 8.4, A.5.2, A.5.3, A.5.4, A.5.5
DOC-OBJECTIVES | AI Objectives and Planning of Changes | procedure | missing | [5 empty] | No | 6.2, 6.3, A.6.1.2, A.9.3
DOC-PEOPLE | Resources, Competence, Awareness and Communication | procedure | missing | [5 empty] | No | 7.1, 7.2, 7.3, 7.4, A.4.6
DOC-DOCINFO | Control of Documented Information | procedure | missing | [5 empty] | No | 7.5
DOC-RESOURCES | AI Resources Inventory Procedure | procedure | missing | [5 empty] | No | A.4.2, A.4.3, A.4.4, A.4.5
DOC-LIFECYCLE | AI System Lifecycle Procedure | procedure | missing | [5 empty] | No | 8.1, A.6.1.3, A.6.2.2, A.6.2.3, A.6.2.4, A.6.2.5, A.6.2.6, A.6.2.7, A.6.2.8
DOC-DATA | Data for AI Systems Procedure | procedure | missing | [5 empty] | No | A.7.2, A.7.3, A.7.4, A.7.5, A.7.6
DOC-COMMS | Information for Users and Interested Parties | procedure | missing | [5 empty] | No | A.8.2, A.8.3, A.8.4, A.8.5
DOC-USE | Responsible Use of AI Systems | policy | missing | [5 empty] | No | A.9.2, A.9.4
DOC-THIRDPARTY | AI Suppliers, Customers and Third Parties | procedure | missing | [5 empty] | No | A.10.3, A.10.4
DOC-AUDIT | Monitoring, Measurement and Internal Audit Procedure | procedure | missing | [5 empty] | No | 9.1, 9.2
DOC-REVIEW | Management Review Procedure | procedure | missing | [5 empty] | No | 9.3
DOC-IMPROVE | Nonconformity, Corrective Action and Improvement | procedure | missing | [5 empty] | No | 10.1, 10.2

## Review actions
(Example Client) · ISO 42001 · generated from the GRC record as of 2026-10-24. Read-only export: change the record through pull requests, not here.
Review | Action ID | Action | Owner | Due | Status | Closed | Evidence