# (Example Client) ISO 42001 Project Brief

Analyst Orientation | Certification readiness and gap closure | 2026-2027

TLDR: Help (Example Client) turn an existing set of AI practices and technical controls into a complete, auditable AI management system (AIMS).

# 1. Client Overview

- (Example Client) is a 160+ person digital-services company founded in 2017. It researches, designs, builds, and modernizes digital products and services.

- Its work spans government, nonprofit, and selected commercial partners, with a strong focus on public-interest technology, healthcare, and Veterans services.

- Publicly identified government customers and partners include the Department of Veterans Affairs, CMS/HHS, IRS, OPM, and other federal programs.

- The company combines product management, research, design, engineering, strategy, and delivery services.

# 2. AI Usage

- (Example Client) is actively adopting and designing AI technology and has published Responsible AI principles centered on stewardship, intentionality, human agency, impact, accountability, privacy, and security.

- The certification scope is focused on the Innovation and Platform teams' building and provision of AI products - not the entire company's general end-user AI use.

- Their documents describe 4 AI systems, 9 SDLC AI tools, 10 infrastructure services, a model registry, and a 19-item gap register.

- Engineering controls already described include gated evaluation metrics, human approval gates, provenance hashing, fail-closed defaults, production telemetry, PR/CI review, prompt/version controls, and immutable image digests.

# 3. What is already in place

| FOUNDATION | EXAMPLES |
| --- | --- |
| Scope & inventory | Draft AIMS scope; AI systems/tools/infrastructure inventory; model registry. |
| Risk | 20 AI-category risks in Drata with owners, treatments, residual scores, and open actions. |
| Engineering | Lifecycle testing, monitoring, change controls, human approval, agent authority limits. |
| Existing governance | SOC 2 policy suite, enterprise risk process, incident management, vendor program, quarterly leadership review. |
| Corporate AI baseline | Responsible AI Principles and company-wide AI Use Policy for end-user use. |

# 4. Gap Analysis

Treat client readiness statements as hypotheses until evidence shows the control is documented, implemented, evidenced, and operating.

| AREA | WHAT TO VERIFY / CLOSE |
| --- | --- |
| AIMS governance | No producer-scope AIMS AI policy yet; scope draft still needs leadership approval. |
| Impact assessment | No AI impact assessments have been completed; methodology/template must be established and used. |
| Training & competence | AI-specific training is planned but not yet operating. |
| Data governance | Existing classification taxonomy does not yet cover AI artifacts such as corpora, datasets, checkpoints, and delivered models. |
| AI suppliers | AI-specific suppliers have not yet been run through the existing vendor program; supplier contract/DPA requirements are incomplete. |
| Control codification | Some human-review and engineering practices operate in code/process but are not fully reflected in policy text. |
| Regulatory mapping | Formal per-market AI regulatory/contractual mapping has not yet been performed. |
| Internal audit | No standalone AI/AIMS internal audit program or completed AI-scoped internal audit exists. |
| Management review | AI is discussed in quarterly leadership review, but a dedicated standing AI/AIMS review structure needs to be formalized. |

## Analyst evidence test

- Documented — Is the requirement formally defined?

- Implemented — Is the process actually in use?

- Evidence exists — Can (Example Client) produce records showing execution?

- Tested — Does sampling/interview evidence support consistent operation?

## Readiness snapshot (as of 2026-10-22)

0 of 65 applicable requirements pass all four tests; 12 gaps open; 5.8% of evidence-test legs verified. Generated from the engagement repository - do not edit by hand.

| TEST | VERIFIED | PARTIAL | CLAIMED | NOT STARTED |
| --- | --- | --- | --- | --- |
| Documented | 2 | 13 | 9 | 41 |
| Implemented | 8 | 10 | 8 | 39 |
| Evidence exists | 5 | 3 | 0 | 57 |
| Tested | 0 | 1 | 0 | 64 |

# 5. Timeline

| MONTH | OBJECTIVE | DELIVERABLES |
| --- | --- | --- |
| OCT 2026 | Validate & establish | • Kickoff and owner alignment • Validate gap-analysis claims and evidence • Finalize AIMS/certification scope • Build clause/control matrix and remediation tracker • Confirm certification-body milestones |
| NOV 2026 | Build governance | • Approve AIMS/AI policy • Formalize roles, objectives, risk and impact methodology • Define AI data classification and supplier requirements • Codify lifecycle and human-oversight requirements |
| DEC 2026 | Implement & evidence | • Complete initial AI impact assessments • Run AI supplier reviews and address contract gaps • Launch AI-specific training • Operationalize governance cadence and collect evidence • Close implementation findings |
| JAN 2027 | Test the AIMS | • Perform ISO 42001 internal audit • Verify inventory, risk register and impact assessments • Complete corrective actions • Conduct formal management review • Prepare certification evidence package |
| FEB 2027 | Stage 1 | • Run readiness/mock audit • Close internal-audit findings • Evidence cleanup and owner preparation • Support Stage 1 audit • Triage Stage 1 findings |
| MAR–APR 2027 | Stage 2 & closure | • Close Stage 1 findings • Prepare process owners for interviews • Support Stage 2 audit • Respond to findings and corrective actions • Certification-body closure / issuance contingency |

# 6. Needs

- Maintain the clause/control mapping, evidence index, remediation tracker, owner, due date, and status.

- Review submitted evidence against the four-part evidence test; flag unsupported or ambiguous readiness claims.

- Draft and revise policies, procedures, templates, and workpapers for lead review - do not invent operating practices.

- Support AI impact assessments and supplier reviews by gathering evidence, pre-populating factual sections, and tracking actions.

- Prepare test samples, record objective evidence, and document exceptions for the internal audit.

- Organize Stage 1/Stage 2 evidence so an auditor can trace each requirement to a current, approved artifact or record.

## Working rule

If a control is described but you cannot trace it to an owner, current artifact, and operating evidence, treat it as unresolved and escalate it to the engagement lead.

# 7. ISO Requirements

- AIMS scope, governance, objectives, policies, roles, and responsibilities are approved and understood.

- AI inventory, risks, impact assessments, supplier controls, lifecycle controls, and training are current and evidenced.

- Required processes have operated long enough to produce credible records for auditor sampling.

- Internal audit has tested the AIMS; findings have owners and corrective actions.

- Management review has considered AIMS performance, risks, audit results, changes, resources, and improvement actions.

- Stage 1 findings are closed or controlled before Stage 2; process owners can explain what they do and show evidence.

# 8. Engagement Guardrails

- 200 total consulting hours: protect time for January testing and certification support.

- (Example Client) owns implementation and evidence production; our team structures, reviews, tests, and challenges.

- Use existing SOC 2 processes where they genuinely satisfy AIMS requirements rather than creating parallel processes.

- Prefer durable, auditable processes over one-time documents created solely for certification.

- Escalate scope changes, major control redesign, legal/contract questions, or unsupported high-risk claims to the engagement lead.

# 9. Key Risks

- Overstated readiness or evidence that reflects design rather than operation.

- Late implementation that leaves too little operating history before Stage 2.

- Slow SME responses, policy approvals, vendor reviews, or contract decisions.

- Internal-audit or management-review slippage.

- Scope creep consuming the 200-hour budget.

- Certification-body scheduling or findings pushing issuance into April.